## Sheet1
ACTION | SPECIFIC | MEASURABLE | APPROPRIATE | REALISTIC | TIME | STAFF RESPONSIBLE | STATUS
Conducting research about sustainability | Qualitative: 3 focus groups with 5-10 participants, Quantitative: catering survey | A clear dataset that will be able to inform the institution and union about what students would like to see in terms of sustainability on campus | Yes, there is a definite need to understand students' attitudes towards sustainability | Yes, focus groups part of council and executive committee meetings, pizza provided, vouncher to Ethical Shop provided to societies focus group | 9th March, 14th March, 16th March | Kata, Ryan | All focus groups done, needs writing up
Student Rep and Society Leaders Training | 1.5 hours long training about SDGs, covering sustainability in formal curriculum, main sustainability campaings | Attendance, survey afterwords, keeping in touch with students leaders to see what help they need, whether they started engaging with professors, students | Training is, embedding sustainability in curriculum is a long time goal | Yes, there have been training sessions in the last couple of years as well | 11th February | Kata, Tamanna, Dimitri, Arthur | All done
Decolonising City | Engage more students and staff on what has to be changed, what decolonising means, put resources on the website, ogranise panel | Attendance, engagement with the campaign | Decolonising the curriculum is a crucial movement in all universities | Ambitious, one step at a time | All year campaign | Raquel, Shahd | Panel was successful, recourses are on the website
Keeping the sustianbility website updated | Always having useful information on the sustainability website with up-to-date events | Website content | Yes | Yes | All year - during Reuse, Reduce & Research Campaign - make main banner sustainability related | Kata, Josh | Needs constant updating
Sustainability training for staff | Training on sustainability campaigns the union could join in the future, training on energy efficiency, sustainable fashion and other behaviour change tips | Survey, whether the Union joined any mentioned campaigns, changes in staff behaviour | Yes | Yes | March-April (during one of the team meetings | Kata | Training delivered on 20th April
Fair trade | Union Shop offers fair trade items, union actively supports fair trade | Monitoring fair trade sales | Yes | Yes | All year | Chris | Union is offering fair trade items but could look into how to offer even more
Having a sustainability award | Helping societies and students showcase their sustainability work | Number of nominations, quality of nominations | Yes | Yes | Award date: 12th May | Dimitri | We have a sustainability award which received
Working on the sustainability policies put forward by students | Ensuring that the sustainability related policies get implemented including the 'Invest for Change' policy, the 'Free reusable water bottles' policy and the 'Halal, vegan and healthy food in cafes' policy | Meeting concerning the policies, action put forward | Student policies are a crucial part of the Students' Union's inner democratic working | Some policies are ambitious, but in smaller steps, achievable | Throughout the whole year | Kata, Raquel | the Students' Union is working on policies put forward by students
Union's most significant negative impacts | Identifying our negative impacts of the environment in order to improve in the future | The production of a comprehensive report | Yes | Mostly yes, although the Union does not have access to its own energy bill, as we do not have our own building | April | Kata | Needs assessment
Mental health campaign | To implement one of the student policies, the Study Well Campaign will be launched more than one time a year. The purpose of the Study Well project is to support students to thrive academically and keep their wellbeing throughout the year, with particular focus on assessment periods. | How populated the study well weeks are in terms of events, attendance on events, higher student satisfaction (surveys) | A strong focus on student mental health and welbeing is crucial, espceially during the exam period when they are likely to be more anxious | Yes, 3-4 events every day | Main periods: December, January, May-June | Tamanna, Kata | December and January periods were successful, May-June period is starting soon
Reduce reliance on fossil fuels | To start a convesation with the insitition about its invesment policies, review City's Sustainable Investment Statement and compare it to SOS' 5 key policy asks | How the meeting goes with the instiution, whether there will be changes to wehere City invests | It is critical for universities to invest in students' future and act in the interest of them, not against | Yes, through several emails and meetings, it is important to establish a good, cooperative relationship | March: introduction email, booking in a meeting, specifying asks April: meeting with Mel from SOS to review asks April-May: meet with Marion (Chief Financial Officer) | Louis | Louis started a conversation with Marion via email
COP26 | Engage students with COP26, advertise it on several different platforms | How many articles, posters are up, clicks on the article | Yes | Yes | September-October 2021 | Hannah | Several articles are up on the Union's and university's website, roller banners are up in the Pavilion
Sustainability/Green Impact working group | Setting up a Green Impact/sustainability working group to work on the Students' Union' sustainablity events, initiatives | The working group meets every second week, its effectiveness can be measured in how many events are created, and how good the cooperation between the members are | Yes | Yes | Every second week from January until April | Everyone | The group is meeting regularly and is working effectively
Collaborating with liberation groups and officers | Discussing how all liberation groups can be included in the Union's sustainability-related events, and what barriers might specific liberation groups face | Good data on the mentioned questions and in engagement of liberation groups in the long term | Yes, very important to understand the viewpoint of a more diverse community, not only the 'WEIRD' population | Collaboration is definitely realistic, high engagement is more ambitious but still achieveable | During the sustainability research - March | Kata, Raquel | We have valuable data from the focus group conducted during an Executive Committee meeting where several liberation officers were present
CAMPAIGN
Advertising | Create campaign page for the website, Make the main banner advertise the campaign on the main SU page, Advertise the campaign on the sustainability page, Advertise the campaign on in SU student newsletters, Advertise campaign in the university’s sustainability newsletter, Create and print posters | How many articles, posters are up, how many students engaged with the events | Advertising the campaign is crucial | Yes | From the start of April | Kata, Josh | Campaign is over
Workshop: Design your own tote bag | A workshop for students to reduce their plastic bag use by designing their own tote bags, Confirm time and place, Use City’s tote bags, Use paint in the office, No finances | How many students showed up, feedback from students | Students expressed a need for more arts-and-craft kind of events | Yes | 11th April | Kata | Campaign is over
Vintage kilo sale | Collaboration with Vintage Vera, Conduct risk assessment, Arrange it with PAF, No finances | Attendance, how successful was it for Vintage Vera | Yes | Yes | 8th April | Kata | Campaign is over
Don’t Be a Dummy, Win the Honey Quiz | Put together quiz, Book stall on university walkway, Get honey from sustainability team, No finances | Get at least 30 students fill out the quiz, students’ report that their knowledge of sustainability issues including Fairtrade, Sustainable fashion and energy efficiency | Yes | Yes | 12th April | Kata | Campaign is over
Invest for Change Workshop | Arrange session with Mel from SOS, Book room | Students attending feel more empowered, they start interacting with the university | Yes | Yes | 12th April | Kata | Campaign is over
Gardening Session | Collaborate with Arthur from the Sustainability team, Put together session on the Sustainable Food Guide of SOS | More sign-ups to the gardening sessions, more knowledge about sustainable food | Yes | Yes | 14th April | Kata, Arthur | Campaign is over